## Material List
Rocket
Item | # | Material | Sources
Nose cone | 1 | Madcow 4" plastic | Madcow Rocketry, P/N PNC40Y
Body tubes | 2 | 4" Blue tube | Apogee components, Balsa Machining, Always Ready Rocketry
Coupler | 1 | Full-length 4" BT coupler | Apogee components, Balsa Machining, Always Ready Rocketry
Motor mount | 1 | 54 mm Blue Tube | Apogee components, Balsa Machining, Always Ready Rocketry
Centering rings | 2 | 1/4" (6mm) aircraft plywood | Apogee components, Always Ready Rocketry
Avbay tube bulkheads (outer) | 2 | 1/4" (6mm) aircraft plywood | Apogee components, Always Ready Rocketry
Avbay coupler bulkheads (inner) | 2 | 1/4" (6mm) aircraft plywood | Apogee components, Always Ready Rocketry
Plywood for fins, NC, sled, etc | 1 | 1/4" (6mm) Finnish birch plywood, 2' x 4' sheet | Aircraft Spruce, P/N 02-20850
NC Bulkhead | 1 | 1/4" (6mm) Finnish birch plywood | Make from stock
Fins | 3 | 1/4" (6mm) Finnish birch plywood | Make from stock
Avbay sled | 1 | 1/4" (6mm) Finnish birch plywood | Make from stock
Thrust plate/motor retainer | 1 | 1/4" (6mm) Finnish birch plywood (2-ply) | Make from stock
Recovery gear
Shock cord, booster & payload | 20 yds | 1/4" tubular kevlar, 3600 lb test | Top Flight Recovery
Nomex Chute protectors | 2 | 12" Nomex | Top Flight Recovery
Drogue Chute | 1 | 18" Nylon | Top Flight Recovery, Fruity Chutes
Main Chute | 1 | 48" toroidal | Fruity Chutes, believe you have on already?
Hardware
Avbay rods | 2 | 1/4"-20, 22", Stainless | McMaster-Carr
Eyebolts | 4 | 1/4-20, 1" long, 500 lb | David will provide
Quicklinks | 6 | 1/4" dia, 1400# load limit | David will provide
Nuts, washers for eyebolts/rods |  |  | David will provide
Screws for flight computer mounting |  | 316 SS Pan Head Phillips screw, 4-40, choose length | McMaster-Carr
Spacers for flight computer mounting |  | Nylon unthreaded round spacer, 3/16" OD, 9/32" long, #4 screw | McMaster-Carr
Nuts for flight computer mounting |  | 18-8 SS Broach style captive nuts,4-40, 0.060 panel thickness | McMaster-Carr
Electronic components
Terminal blocks for ematches | 4 | 2 pos, 5.08 mm, PCB | David will provide
Internal wiring |  | 24 gauge | David will provide
Internal wiring connectors | 4 | 3M locking plug/socket | David will provide
Switches | 2 | Aerocon or Featherweight screw switches, or Schurter (voltage select) style | Aerocon Systems
9v Battery holder | 2 | Plastic, solderable leads, screw mounted | Missile works

## Timeline
Letter code | Section |  | Red | Bulkheads/Centering rings/slot cutting (band saw/router work)
A | Booster |  | Blue | Tube/coupler/NC cutting (radial/table saw)
B | Nosecone |  | Green | Fins/avbay sled cutting (radial/tablesaw)
C | Avionics bay |  | Yellow | Epoxy/gluing (stable workspace)
D | Avionics sled |  | Purple | Hole drilling (drill press)
E | Payload |  | Orange | Soldering
Build Session | 9-Feb pm | 10-Feb am | 10-Feb pm | 11-Feb am | 16-Feb pm | 17-Feb am | 17-Feb pm | 18-Feb am | 2-Mar pm | 2018-03-03
Tasks
| A1 | A7 | A11y | A11z | A12 | A13 | A14 | A15 | A18 | Launch!
| A2 | A8 | B4 | B6 | B6 | B6 | B6 | A16 | E2
| A3 | A9 | B5 | C8 | C9 | C11 | D6 | A17 | E3
| A4 | A10 | B6 | D1 | C10 | D6 | D7 | B7
| C1 | A11x | C4 | D2 | D6 | D7 | E4 | D8
| C2 | A6 | C5 | D3 | D7 |  |  | D9
| E1 | C3 | C6 | D4
| A5 | B2 | C7 | D5
| B1 | B3

## Booster
Build plan
A | Booster Construction
Step | Description | Dependencies | Notes
A1 | Cut motor mount tube to length
A2 | Cut MMT centering rings/drill for recovery attachment
A3 | Epoxy fwd centering ring to mmt | A1, A2
A4 | Cut body tube to length
A5 | Mark and cut fin slots | A4
A6 | Cut thrust plate
A7 | Mount recovery attachment | A3
A8 | Epoxy MMT to booster | A7
A9 | Cut fins
A10 | Shape fins (if desired) | A9
A11 | Epoxy fins to booster | A10 | Multi-step, do 1 fin at a time (designate as A11x, y, and z)
A12 | Apply internal/external fillets to booster | A11 | Multi-step, fillet one area at a time
A13 | Epoxy rear centering ring in place | A12
A14 | Mark and drill rail button locations | A13
A15 | Mount rail buttons | A14
A16 | Drill 1/8" pressure relief hole | A15
A17 | Mount thrust plate/motor retainer. | A13
A18 | Mount avbay and drill/tap 3 2-56 shear pin holes | A17, C11

## Nosecone
Build plan
B | Nose cone construction
Step | Description | Dependencies | Notes
B1 | Remove bottom of NC to open up interior
B2 | Cut NC bulkhead and reinforcement ring | B1
B3 | Glue bulkhead to reinforcement ring | B2
B4 | Fit bulkhead to NC | B3
B5 | Drill mounting holes for bulkhead to NC attachment | B4
B6 | Construct NC avionics sled for GPS tracking | B5 | Steps here will depend on design of NC tracking setup
B7 | Attach NC eyebolt for recovery

## Avionics bay
Build plan
C | Avionics bay construction
Step | Description | Dependencies | Notes
C1 | Cut avbay coupler to length
C2 | Cut switchband
C3 | Cut avbay bulkheads and recess lip
C4 | Drill holes in bulkheads for threaded rod and eyebolts | C3
C5 | Drill holes in bulkheads for terminal block wires | C3
C6 | Solder leads to bulkhead terminal blocks |  | need 4 terminal blocks
C7 | Epoxy terminal blocks to bulkheads | C3,C6
C8 | Seal terminal wiring holes with epoxy | C7
C9 | Attach quick-connects to terminal wires | C8
C10 | Coat external surface of bulkheads with thin layer of epoxy | C9 | Protection from ejection charges
C11 | Drill vent holes/switch access holes in switch band | D9 | Need completed sled to properly line up holes

## Avionics sled
Build plan
D | Avionics sled construction
Step | Description | Dependencies | Notes
D1 | Cut sled wood to size | C3 | Need correct length from avbay construction
D2 | Drill sled for all mounting and wiring holes | D1 | Need holes for flight computers, battery mounts, experimental setup, etc. Cut notches if necessary for switches.
D3 | Mount and secure all clinch nuts | D2
D4 | Drill and cut threaded rod mounting guides |  | These are the wood guides that hold the sled to the allthread
D5 | Attach rod guides to sled | D3,D4
D6 | Attach other needed supports to sled | D5 | This will be very dependent on experimental equipment design
D7 | Mount all equipment to sled | D6
D8 | Route all necessary wiring (batteries, terminals, etc) | D7
D9 | Attach connectors for ematch terminal connections | D8

## Payload
Build plan
E | Payload construction
Step | Description | Dependencies | Notes
E1 | Cut Payload tube to length
E2 | Mount NC and drill/tap 3 2-56 shear pin holes | E1, B7
E3 | Mount avbay and drill 3 rivet attachment holes | E1,C11
E4 | Drill 1/8" vent hole